## Slide 1
DWG-001 · PROJECT KICKOFF
PROJECT ATLAS
Replace warehouse software across 4 sites by October 2027.
LEAD
Arjun Pillai · Supply Chain & IT
DATE
03.03.27
REV
A
SHEET
01 / 08
Notes: Fills from: project name, one-line goal, project lead, team, kickoff date.

## Slide 2
02 · WHY NOW
The old system is the bottleneck
CURRENT
2014 warehouse system
3.5 hrs
picking delay at peak
2.8%
orders with the wrong item
Dec 2027
vendor support ends
SHEET 02 / 08
Notes: Fills from: the current system or process, and up to three problems it causes with a number each.

## Slide 3
Scope
03 / 08
IN SCOPE
[x] Inventory & picking, 4 sites
[x] Scanners for 220 staff
[x] Order system integration
[x] Training & go-live support
OUT OF SCOPE
[ ] Transport & fleet tracking
[ ] Finance & invoicing
[ ] New warehouse locations
Notes: Fills from: up to five in-scope and up to four out-of-scope items.

## Slide 4
Who owns what
04 / 08
SPONSOR
Lakshmi Nair · COO
PROJECT LEAD
Arjun Pillai
TECH
Farhan Qureshi
SITES
4 warehouse heads
TRAINING
Sneha Joshi
VENDOR
StackWare
Notes: Fills from: sponsor, project lead, and up to four workstream owners with their team.

## Slide 5
Plan · Mar to Oct
05 / 08
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
Requirements
Configuration
Data migration
Pilot · Bhiwandi
Rollout · 3 sites
Switch off old system
Notes: Fills from: up to six workstreams with start and end month, and key milestone dates.

## Slide 6
Risk matrix
06 / 08
LIKELIHOOD →
IMPACT →
A
B
C
D
A
Festive peak overlaps rollout
Freeze go-lives 10 Oct – 15 Nov
B
Data migration errors
Two dry runs per site
C
Staff new to scanners
Floor champions trained early
D
Vendor team changes
Named leads in contract
Notes: Fills from: up to five risks, each with likelihood, impact and a mitigation.

## Slide 7
A typical project week
07 / 08
MON
10:00
Stand-up, 30 min
TUE
ALL DAY
Site visits
WED
15:00
Vendor sync
THU
FOCUS
No meetings
FRI
16:00
Status note to sponsor
TOOLS · Jira, shared Drive
DECISIONS · Lead decides, sponsor breaks ties in 48 h
Notes: Fills from: recurring meetings with day and time, tools used, and decision rule.

## Slide 8
Action log
08 / 08
ID
ACTION
OWNER
DUE
A-01
Send requirements template to site heads
Arjun
05.03
A-02
Sign vendor statement of work
Lakshmi
07.03
A-03
Export current inventory data
Farhan
10.03
A-04
Pick floor champions at each site
Site heads
14.03
Notes: Fills from: up to five immediate actions with owner and due date.